Chicago Rehab Network

Department of Housing Quarterly Analysis

3rd Quarter 2002

“What is happening with affordable housing is, say you are building a home and you say to a family this costs $175,000 to $200,000. The couple looks at you and they are working, and they say, ‘What? $200,000 or $175,000?’…We have to get that number down so that if they are both working for let us say $11, $12, or $14 an hour and have two or three kids, how are they going to afford that?  That is the issue.”

Mayor Richard M. Daley

December 4, 2002

Report Summary

- Chicago is still in the midst of a housing crisis. According to Census 2000, Chicago has a shortage of 49,077 apartments affordable to very low-income renters. The 2,814 rental units that the Department of Housing (DOH) has supported this year for families earning under 30% is a start – but not nearly enough to address the housing crisis. The number of Chicago families paying too much of their incomes for housing is almost as high as it was in 1990, despite tremendous economic growth.

- As of September 30, DOH had $28.6 million, or 9.8% of its budget, sitting unspent.  A close examination reveals that some programs are largely unused, like HomeStart, the Bungalow programs and City Mortgage.  It should be considered whether or not those purchasers with incomes over 80% of median might qualify for standard mortgage products.  Further, we submit that unallocated program dollars be reallocated to the highest priority housing need.

- Westhaven Park, part of the redevelopment of Henry Horner Homes, is costing the city $224,555 per unit –more than the $195,000 per unit comparable condos at Stateway Gardens’ redevelopment.  Public money should go to subsidize the construction of affordable housing, not market rate housing. We ask that CHA and DOH and DPD fully report on how public money is being spent at redevelopment sites in order to better understand the costs and benefits of mixed income development.

- The city’s most productive program for building for-sale affordable housing has created hundreds of units – but costs the city nothing.  This is not New Homes for Chicago, but the Chicago Partnership for Affordable Neighborhoods (CPAN) which provides municipal incentives for market-rate condominium developers who set aside affordable units.

Finally, the success of CPAN in harnessing the private market’s potential to create affordable housing demonstrates that an affordable housing set-aside can indeed work in Chicago.  Had the ordinance introduced by Ald. Toni Preckwinkle and 16 other Alderman on December 3rd been in force over the last 10 years, Chicago residents would benefit from over 8000 units of quality affordable housing.

Production Overview:

|  | Resource % of 2002 Goal | Units Percentage of 2002 Goal |
| --- | --- | --- |
| Multifamily Housing | 49% | 76% |
| Single Family Housing: Reported Public Funds Only | 45% 38% | 64% |
| Improvements | 47% | 55% |

| Units Created By Income |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 0-15% AMI | 16-30% AMI | 31-50% AMI | 51-60% AMI | 61-80% AMI | 81-120% AMI | Total Units |
| Multi-Family | 1659 | 1155 | 1026 | 172 | 102 | 7 | 4121 |
| Single-Family | 0 | 13 | 321 | 270 | 360 | 341 | 1310 |
| Improvements | 1782 | 1685 | 1959 | 508 | 552 | 431 | 4020 |

As of September 30, DOH had $28.6 million, or 9.8% of its budget, sitting unspent.  Several DOH programs are short of reaching their spending and unit goals. In particular, two major homeownership programs have not seen any use at all so far this year: HomeStart, with a $20 million budget, and the Bungalow Rehab Tax Credit, with a $2.4 million budget. These programs should be re-evaluated for utility and, if necessary, integrated into programs that could use the same funds more efficiently.

A few highlights in terms of funds committed:

- Only 33% of tax credit equity has been committed as of 9/30/02, compared to 74% during the same period in 2001.

- 49% of multifamily development resources have been committed as compared to almost 70% during 2001.

- Two DOH programs --City Mortgage and the Bungalow Program—are being largely used by families/individuals making over 80% of median income.  These homebuyers can qualify for unsubsidized mortgages. Indeed, the Bungalow Program has been quite successful at matching bungalow owners with private-market financing.  Since 2000, the Bungalow Program has provided only four owners with City Mortgage subsidized rehab loans while 109 have accessed bank loans for rehab.

The original 1999-2003 Affordable Housing Plan, in fact, limited the major homeownership program eligibility to those making under 100%, when in fact the Quarterly reports break down units created up to 120% of median income.  In light of the results from Census 2000, we believe that scarce public resources should be targeted much more carefully and strategically to create quality affordable housing.

Howare these in the units by income numbers in comparison to plan?

Do the multifamily numbers include units getting rental subsidy?  Or development alone?

Rent Burden:

We have done an extensive examination of Census 2000 statistics in preparation for the release of the CRN Affordable Housing Fact Book, and have found that while the 1990s were a busy and exciting decade for Chicago, the city still faces great challenges in meeting its housing needs. Rent burden (percentage of renters paying more than 35% of their income towards rent) in the city has indeed declined – but only by three percentage points, during a decade of astonishing economic growth. Meanwhile, the number of homeowners burdened by housing costs grew by 38.3% over the decade. Indeed, nearly a quarter million Chicago households pay more than 35% of their income towards housing – an imperceptible drop of only 1.7% over 1990.

Disparate Neighborhood Impacts:

Only part of the city shared in the  boom of the 1990s. We know from our housing analysis by ward, soon to be published in the 2003 Affordable Housing Fact Book, that every community in the city has very specific housing needs and challenges.  Although 52,042 new housing units were built in the city during the 1990s, over half of those new units were in just eight of the city’s 77 community areas: Lake View, Lincoln Park, Logan Square, Near North, Near South, Near West, Uptown, and West Town.  Even though homeownership increased by 4.9% in the 1990s, foreclosures increased by 74% just between 1993 and 2001. And although the city issued 18,257 new construction permits between 1993 and 2002, the city also issued 15,970 demolition permits. And yet, 53,313 abandoned buildings still haunt Chicago’s streets, a sure sign of continued disinvestment– and over half of the abandoned buildings are in just eleven community areas.

| Homeownership rate in 1990s | +4.9% | Foreclosures initiated in 1990s | +74% |
| --- | --- | --- | --- |
| Construction permits issued in 1990s | 18,257 | Units demolished in 1990s | 15,970 |
| New Housing Units Built in 1990s | 52,042 | Abandoned units | 53,313 |

Sources:	Census 2000, Department of Planning and Development, National Training Information Center

Rental Housing Supply:

Our analysis also shows that, in 1999, there were 221,201 renter households in Chicago with incomes below $20,000 (roughly 30% of AMI). These renters were competing for 172,124 units with affordable rents —creating a shortfall of 49,077 units. The 2814 rental units that DOH has supported this year for renters making less than 30% of AMI address less than 6% of this crisis and assist just 1.27% of the renter households in this most needy of income brackets. DOH has funded the construction or rehabilitation of 629 rental units for extremely low-income families this year.  The large gap illustrated below points to the need for identification of new resources and disciplined targeting of existing resources.

Project Cost Comparison:

51st & King Apartments. The city’s leadership in preserving and rehabilitating this property – a historic building that provides affordable housing for large families – is commendable. However, just half a mile from this success story, the 451 units at the Rosenwald Garden Apartments – in buildings nearly identical to 51st & King – sit vacant and threatened with demolition. The city should uphold Julius Rosenwald’s dream of building affordable housing for Chicago’s African Americans and take the lead in finding resources to rehabilitate this landmark. Rehab costs for this project are at about $90000 per unit.

Westhaven Park (Horner Redevelopment). We were alarmed to find that total per-unit costs at Westhaven Park will reach $224,555 per unit – even though the site is free. Construction costs alone amount to $173,365 per unit. These costs are far in excess of what is customary to ensure quality construction for rental housing.  Comparable market-rate for-sale units at the redeveloped Stateway Gardens will average $190,000-195,000. It is likely that public funds are paying for demolition and site preparation work for both affordable and market-rate units. Market-rate units at CHA redevelopment sites should pay their own way, instead of using up scarce public resources.

To get a better understanding of how cost-effective the mixed-income redevelopment of CHA sites is, the Chicago Rehab Network requests that DOH more fully report project financials for these projects. In particular, published project financial summaries should include costs and prices for all units, market-rate and affordable, rental and for-sale. Furthermore, cost itemization should provide more detail of “Residential Construction” as a single line item and separate site preparation from construction.  Given the scarcity of resources and the vast need for rental housing, we request a full accounting of all city resource commitments to public housing redevelopment.

CPAN

Chicago Partnership for Affordable Neighborhoods (Welbourn Row, 950 W. Monroe).

We are encouraged that CPAN has rapidly grown into DOH’s single largest single-family rehab & new construction program, creating 151 units this year without requiring significant outlays from city coffers. This figure indicates that the private market can and will leverage significant new resources for affordable housing.

As we have mentioned in prior quarters, we do not believe that developer money committed to CPAN in the form of write-downs should be counted against DOH’s budget of public dollars towards housing. As reported in the DOH report, CPAN contributions account for 86.4% of DOH’s 2002 spending on single-family rehab and new construction.  Looked at without CPAN to date, DOH has only spent 4.9% of its $24 million budget for single-family rehab and construction.  Developer contributions should be tracked, but not as an offset to public dollars

.

In the future, the city as a whole should more fully report on CPAN activities. A full list of sites and developers offering affordable units under CPAN, along with project financial reports and an itemized list of units committed and incentives granted, should be included in each DOH quarterly report. Such accountability will help to ensure that public resource equitably and efficiently support development, and to adequately evaluate the program’s effectiveness.

DOH recently proposed to follow Boston’s lead in requiring all city-financed projects to include affordable housing. Boston requires that all large residential developments subject to discretionary planning review also set aside 10% of units as affordable housing. If a similar 10% set-aside had been in place for just all Planned Developments approved by the Plan Commission since 1999, at least 2,118 affordable housing units would have been committed by those large projects – in addition to the hundreds of units already committed by developers of Planned Developments, like Kingsbury Park

We are in support of the general thrust of this ordinance introduced by the Department of Housing on November 25.  Most large cities have policy that ensures that public, city-owned resources be leveraged and targeted towards housing for those who need it most, rather than into market-rate units.  Though we would recommend several clarifications to maximize impact, we are pleased that this often-used practice would be codified into law.

On December 3, 17 Alderman introduced legislation to directly address the critical lack of affordable housing in Chicago.  A 25% set-aside will create affordable housing in all private market rate developments over 10 units.  The attached map shows the housing that would have been created in the City if this policy had been in force over the last 10-year period.  With the addition of 50000 units over the last decade, over 8000 affordable units would now be available to Chicago residents.  It is without question a bold move, but not unprecedented and not untested in other big cities.  Large scale for profit developers realize that their success relies on the service sector and their employees and vendors being able to find quality affordable housing.  The future economic strength of our City requires this kind of visionary leadership.  This is Valuing Affordability.